## Definitions
Definitions
Metric | Abbrev. | Description | Formula/Value
Budget at Completion | BAC | Baseline cost for 100% of project.
Actual Cost | AC | Total costs actually incurred so far.
Earned Value | EV | Amount of budget earned so far based on physical work accomplished, without reference to actual costs.
Planned Value | PV | The budget for the physical work scheduled to be completed by the end of the time period.
Cost Variance | CV | Measure of cost overrun. The difference between the budget for the work actually done so far and the actual costs so far. | Earned Value–Actual Cost EV–AC
Cost Performance Index | CPI | Cost efficiency ratio. A CPI of 1.0 means that the costs so far are exactly the same as the budget for work actually done so far. | Earned Value/Actual Cost EV/AC
Schedule Variance | SV | Measure of schedule slippage. The difference between the budget for the work actually done so far and the budgeted cost of work scheduled. | Earned Value–Planned Value EV–PV
Schedule Performance Index | SPI | The schedule efficiency ratio. An SPI of 1.0 means that the project is exactly on schedule. | Earned Value/Planned Value EV/PV
Estimate to Completion | ETC | The expected additional cost to complete the project. | Estimate at Completion–Actual Cost EAC–AC
Estimate at Completion | EAC | Expected total cost based on the current cost efficiency ratio. | Budget at Completion/Cost Performance Index BAC/CPI
Status |  | Average of CPI & SPI | (Cost Performance Index+Schedule Performance Index)/2 (CPI+SPI)/2
|  | GREEN = On track | >1.0
|  | YELLOW = Slightly behind schedule or over budget | >0.85
|  | RED = Needs immediate attention | >0.65
|  | BLACK = Killed or Restore | <0.65

## Forecasting Report
Programme Forecasting Report
programme Name:
Department:
programme Manager:
programme Completion Date:
Schedule and Cost
Budget at Completion (BAC) |  |  | Estimate to Completion (ETC)
Earned Value (EV) |  |  | Estimate at Completion (EAC)
Actual Cost to Date (AC) |  |  | Cost Variance (CV)
Planned Value (PV) |  |  | Schedule Variance (SV)
Cost Performance Index (CPI)
Schedule Performance Index (SPI)
Status (Average of CPI + SPI)
Milestones
Milestones |  | Planned Finish Date | Actual Finish Date | Variance (Days) | Status (G/Y/R)
Milestone A: Charter sign-off
Milestone B: Business requirement sign-off
Milestone C: Functional spec. sign-off
Milestone D: Phase gate review
Scope
Phase Number | Description |  |  | Changes at Phase End | Increase or Decrease
Phase 1 | [Defined]
Phase 2 | [Designed]
Phase 3 | [Developed]
Phase 4 | [Tested]
Phase 5 | [Delivered]
Resources
| Effort Required | Effort Expended | Percent of Effort Expended | Estimated Effort to Complete | Variance
Total effort required (hours)
Issues
| Currently Open | Open Last Week | Increase or Decrease | Closed | Past Due
Number of issues |  |  | 0
Scope Changes
Changes Due to | Requested | Approved | Deferred | Rejected | Under Investigation
Business Requirements
Functional Requirements
Technical Requirements
Total changes | 0 | 0 | 0 | 0 | 0
Changes Due to Approved Scope Changes (Estimate)
|  |  | Cost | Effort (hours) | Schedule (days)
Effect of changes (increase or decrease)
Risks
Risks Identified |  |  | Contingency Reserve
Mitigation Plans Developed |  |  | Last Reviewed
Contingency Plans Developed |  |  | Overall Risk (G,Y,R)
Cost of Mitigations
Top 3 Risks
Risk 1:
Risk 2:
Risk 3:
Top 3 Issues
Issue 1:
Issue 2:
Issue 3:
Comments
Submitted by: |  | Date: